## Jira (1)
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (AHA Link)
Task | SAFECDX-6648 | 108715 | [SafeCDx] - Production Security Scan | Luis Simonet | 606f2db620947c0069697ed2 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-11-14 11:25 | 2025-11-14 11:31
QA | SAFECDX-6529 | 108247 | CLONE - CLONE - Test History | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6528 | 108246 | CLONE - CLONE - Content Studio | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6527 | 108245 | CLONE - CLONE - Localization - Confirmation of Translated File | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6526 | 108244 | CLONE - CLONE - Localization - Upload of CSV File | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6525 | 108243 | CLONE - CLONE - Localization - Translation of CSV File | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6524 | 108242 | Localization - Download of CSV File | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6523 | 108241 | CLONE - CLONE - Validate Forms Builder Templates | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6522 | 108240 | CLONE - CLONE - Validate Form Builder Questionnaire | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6521 | 108239 | CLONE - CLONE - Validate Configuration Library: Sign Up Fields | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6520 | 108238 | Validate Configuration Library: Language | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:01
QA | SAFECDX-6519 | 108237 | CLONE - CLONE - Validate Configuration Library: CVML Status | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:00
QA | SAFECDX-6518 | 108236 | CLONE - CLONE - Validate Configuration Library: Analysis Engine | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:40 | 2025-10-31 05:01
Task | SAFECDX-6503 | 108219 | Production Deployment | Luis Simonet | 606f2db620947c0069697ed2 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | New |  | 2025-10-30 07:25 | 2025-11-14 11:29
Task | SAFECDX-6498 | 108212 | DEVOPS - PROD Config PRE BE Deployment | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | In Progress |  | 2025-10-30 07:23 | 2025-11-21 09:03
Task | SAFECDX-6650 | 108714 | [SafeCDx] - Staging FE Deployment | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-14 11:25 | 2025-11-21 09:55
Task | SAFECDX-6649 | 108713 | [SafeCDx] - Staging BE Deployment | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-14 11:25 | 2025-11-21 09:56
Bug | SAFECDX-6647 | 108706 | [SafeCDX] Admin - Forgot Password ¦ The application display 400 error when the Admin is trying to reset the Password | Jeff Miller | 61f19934aeaacb007209706b | Samantha Toolsie | 61a802e3c15977006ae1f840 | Critical | Done |  | 2025-11-14 06:56 | 2025-11-18 08:07
Bug | SAFECDX-6646 | 108704 | [SafeCDX] Admin Console - Localization ¦ The Application should display the Translated Language section flag clearly under the Localization screen | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | Medium | Done |  | 2025-11-13 14:05 | 2025-11-14 12:23
Bug | SAFECDX-6645 | 108702 | [SAFECDx] Admin Console - SysAdmin - Localization - Application should display the Expanded View popup without any UI issue | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-13 10:33 | 2025-11-14 12:26
Task | SAFECDX-6644 | 108698 | [SafeCDx] - Enhancements to POC | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-13 09:13 | 2025-11-18 10:51
Bug | SAFECDX-6642 | 108691 | [SafeCDX] Production - Client App - PDF ¦ The app does not allow to Download Test Report PDF it just shows a "blob" | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-13 06:30 | 2025-11-14 06:44
Bug | SAFECDX-6641 | 108687 | [SafeCDX] Production - Client App - PDF ¦ The app is not loading the Test Record PDF on iPhone - Safari Browser | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-13 06:12 | 2025-11-14 14:55
Bug | SAFECDX-6640 | 108658 | [SAFECDx] Admin Console - SYSADMIN - Forms Builder ¦ The application should display the List of Questionnaire after Submitting a the Form, instead navigating to the Forms Builder Intro screen | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-12 09:37 | 2025-11-13 09:40
Bug | SAFECDX-6639 | 108642 | [SafeCDX] Client App - Take a Test ¦ The application display Blank screen on the First Question when the internet drops while the user click on Take a Test | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-12 07:42 | 2025-11-13 09:28
Bug | SAFECDX-6638 | 108640 | [SAFECDx] Admin Console - SysAdmin - Localization - Application should display the Form name instead of the ID under the Available Substitutions section | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-12 06:59 | 2025-11-18 08:26
Bug | SAFECDX-6636 | 108632 | [SafeCDX] Client App - Take a Test ¦ The application should not display "X" button and the Header 'Test Result' on the Processing Image screen | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-10 18:30 | 2025-11-12 13:36
Bug | SAFECDX-6634 | 108623 | [SAFECDx] Mobile View - Client App - Take a Test - Application should load the camera once we click on the Retry button after the Internet connection is enabled | Patrick Chou | 61e3a23bb134e80070eec4d3 | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-10 11:19 | 2025-11-12 23:02
Bug | SAFECDX-6633 | 108621 | [SAFECDx] Mobile View - Client App - Take a Test - Application should display the error message in Spanish. | Patrick Chou | 61e3a23bb134e80070eec4d3 | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-10 11:15 | 2025-11-12 23:24
Bug | SAFECDX-6632 | 108620 | [SafeCDX] Admin Console - Sys Admin - Edit WorkSpace - No - Reply ¦ The Application is not displaying the 'No-Reply Email' as configured from the Workspace. | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-10 10:38 | 2025-11-12 16:03
Bug | SAFECDX-6631 | 108610 | [SAFECDx] Admin Console - OrgAdmin - Localization - Application does not collapse the expanded categories when the "Collapse All" option is selected. | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-10 00:35 | 2025-11-14 15:21
Bug | SAFECDX-6630 | 108608 | [SAFECDx] Admin Console - OrgAdmin - Localization - Application displays the "Expand All" icon to the collapse all text, and the "Collapse All" icon to the expand all text | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Medium | Done |  | 2025-11-10 00:30 | 2025-11-14 14:05
Bug | SAFECDX-6629 | 108606 | [SAFECDx] Admin Console - OrgAdmin - Localization - Application should display the X Close icon in blue color under the Expanded View popup | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Low | Done |  | 2025-11-10 00:21 | 2025-11-13 10:06
Bug | SAFECDX-6627 | 108583 | [SAFECDx] Admin Console - SYSADMIN - Forms Builder ¦ The application is displaying Error when 'An Error Occurred' when adding a new Question and Submitting the Form | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-07 16:28 | 2025-11-12 09:38
Bug | SAFECDX-6626 | 108581 | [SafeCDX] Admin Console - OrgAdmin - Lock Toggle ¦ The UI of the Lock Translations toggle is not matching Figma | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | Medium | Done |  | 2025-11-07 15:56 | 2025-11-13 09:46
Bug | SAFECDX-6625 | 108579 | [SafeCDX] Admin Console - OrgAdmin - Lock Toggle ¦ The application should display the Lock Banner at the bottom of the screen on the Content Studio Screen | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-07 15:42 | 2025-11-13 09:48
Bug | SAFECDX-6624 | 108575 | [SAFECDx] Admin Console - Sys Admin - Content Studio ¦ The application is not allowing to delete Small Card from the Content Studio | alakh.verma | 712020:43cf0c0e-f711-4b8d-bbf8-7b0b4cafb142 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-07 14:36 | 2025-11-14 12:44
Bug | SAFECDX-6623 | 108571 | [SafeCDX] Admin Console - Localization ¦ The application is displaying 404 error upon clicking on the Back Button from the Localization screen | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-07 13:23 | 2025-11-13 09:33
Bug | SAFECDX-6622 | 108565 | [SAFECDx] Admin Console - Forms Builder - Application should display the Download icon in blue color instead of black color | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Medium | Done |  | 2025-11-07 10:50 | 2025-11-13 13:48
Bug | SAFECDX-6621 | 108563 | [SAFECDx] Admin Console - Localization - Application should clear the previous search results and display the complete list when the Expanded View is closed and reopened | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-07 10:31 | 2025-11-12 09:34
Bug | SAFECDX-6620 | 108561 | [SAFECDx] Admin Console - Localization - Application should display the categories containing matches should automatically expand and categories without matches should remain collapsed (AC #4) | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-07 10:25 | 2025-11-14 14:02
Bug | SAFECDX-6619 | 108559 | [SAFECDx] Admin Console - Localization - Application should display the "Expand All" option below the Search section | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Medium | Done |  | 2025-11-07 10:21 | 2025-11-12 09:30
Bug | SAFECDX-6617 | 108555 | [SAFECDx] Admin Console - SYSADMIN - Forms Builder ¦ The application should not display 'NO TRANSLATION FOUND' on the Forms Builder Questionnaire Title | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-07 09:55 | 2025-11-12 09:00
Task | SAFECDX-6615 | 108545 | FE: Implement Workspace selection in APP | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Ranjith Gunasekaran | 712020:43427ac6-5629-4a58-80bb-1794d92364ab | Low | Done |  | 2025-11-07 07:34 | 2025-11-18 06:10
Bug | SAFECDX-6613 | 108493 | [SAFECDx] Admin Console - Localization - Application should display the Copy icon without cut-off under the Available Substitutions section | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Low | Done |  | 2025-11-06 02:09 | 2025-11-13 07:17
Bug | SAFECDX-6612 | 108492 | [SAFECDx] Client App - Mobile View - Test History - Application displays the order status as "Error" and displayed the "Test Capture Results" with both Error and Negative results | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Critical | Done |  | 2025-11-06 01:34 | 2025-11-10 06:59
Bug | SAFECDX-6611 | 108490 | [SAFECDx] Client App - Mobile View - Test History - Application displays the "Test Capture Results" section, showing the negative text multiple times for each drug. | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-06 01:28 | 2025-11-07 04:24
Bug | SAFECDX-6610 | 108488 | [SafeCDX] Client App - Test History ¦ The application is displaying the Test History Blank for existing user with Test Records | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | Critical | Done |  | 2025-11-05 20:05 | 2025-11-12 08:58
Bug | SAFECDX-6609 | 108486 | [SAFECDx] Admin Console - SYSADMIN - Configuration Library ¦ The application 'Using' and 'Available' sections within the Configuration Library is not matching with Figma | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-05 18:20 | 2025-11-10 13:10
Bug | SAFECDX-6608 | 108448 | [SAFECDx] Admin Console - SYSADMIN - Reporting ¦ The application should display 1st Login for Each user instead displaying Multiple Logins | Veer.Singh | 624744c3247a4b00691e47d0 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-04 18:43 | 2025-11-07 04:39
Bug | SAFECDX-6607 | 108446 | [SAFECDx] Client App - Test History - Application displays the "Processing Image" screen when we try to navigate to the Test History screen | Patrick Chou | 61e3a23bb134e80070eec4d3 | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-04 13:54 | 2025-11-06 09:05
Bug | SAFECDX-6606 | 108444 | [SAFECDx] Client App - Take a Test - Application displays the loading symbol and keeps on loading when we navigate to the Test History screen | Patrick Chou | 61e3a23bb134e80070eec4d3 | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | High | Done |  | 2025-11-04 13:46 | 2025-11-12 06:44
Bug | SAFECDX-6601 | 108412 | [SafeCDX] Client App - Localization ¦ The application is displaying FE Console error '404' when changing the Language from the Login Screen | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-03 09:53 | 2025-11-06 09:07
Bug | SAFECDX-6600 | 108408 | [SafeCDX] Client App - Localization ¦ The application is throwing FE Console error 'qr_code_scan_error": "QR Code Scan Error' when changing the Language from the Menu | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-11-03 09:06 | 2025-11-06 09:08
AQA | SAFECDX-6599 | 108406 | AQA: [SafeCDx] - Localization - Categorization of the Substitutions Menu | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 08:09 | 2025-11-17 22:25
QA | SAFECDX-6598 | 108404 | QA: [SafeCDx] - Localization - Categorization of the Substitutions Menu | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 08:09 | 2025-11-17 01:35
Tuskr | SAFECDX-6597 | 108402 | TUSKR: [SafeCDx] - Localization - Categorization of the Substitutions Menu | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 08:08 | 2025-11-12 09:06
FE Sub-task | SAFECDX-6596 | 108400 | FE: [SafeCDx] - Localization - Categorization of the Substitutions Menu | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 08:08 | 2025-11-06 04:05
BE Sub-task | SAFECDX-6595 | 108398 | BE: [SafeCDx] - Localization - Categorization of the Substitutions Menu |  |  | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 08:07 | 2025-11-12 06:42
UI Sub-task | SAFECDX-6594 | 108396 | UI: [SafeCDx] - Localization - Categorization of the Substitutions Menu | Lucy Duarte | 61d34f77a54af9006960531d | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 08:07 | 2025-11-03 08:38
Task | SAFECDX-6593 | 108394 | Correct deployment scripts to reflect new Release numbering | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-03 07:43 | 2025-11-10 06:07
AQA | SAFECDX-6590 | 108386 | AQA: [SafeCDx] - Create a Forms Builder Intro Page | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:59 | 2025-11-18 06:45
QA | SAFECDX-6589 | 108384 | QA: [SafeCDx] - Create a Forms Builder Intro Page | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:59 | 2025-11-06 08:10
Tuskr | SAFECDX-6588 | 108382 | TUSKR: [SafeCDx] - Create a Forms Builder Intro Page | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:59 | 2025-11-04 02:23
FE Sub-task | SAFECDX-6587 | 108380 | FE: [SafeCDx] - Create a Forms Builder Intro Page | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:59 | 2025-11-05 13:42
BE Sub-task | SAFECDX-6586 | 108378 | BE: [SafeCDx] - Create a Forms Builder Intro Page | Jeff Miller | 61f19934aeaacb007209706b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:58 | 2025-11-03 06:05
UI Sub-task | SAFECDX-6585 | 108376 | UI: [SafeCDx] - Create a Forms Builder Intro Page | Lucy Duarte | 61d34f77a54af9006960531d | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:58 | 2025-11-02 19:00
AQA | SAFECDX-6584 | 108374 | AQA: [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:53 | 2025-11-17 21:59
QA | SAFECDX-6583 | 108372 | QA: [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:53 | 2025-11-14 07:59
Tuskr | SAFECDX-6582 | 108370 | TUSKR: [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:53 | 2025-11-05 10:34
FE Sub-task | SAFECDX-6581 | 108368 | FE: [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:53 | 2025-11-06 10:42
BE Sub-task | SAFECDX-6580 | 108366 | BE: [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:53 | 2025-11-06 06:45
UI Sub-task | SAFECDX-6579 | 108364 | UI: [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Lucy Duarte | 61d34f77a54af9006960531d | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:52 | 2025-11-02 18:57
AQA | SAFECDX-6578 | 108362 | AQA: [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:48 | 2025-11-17 22:10
QA | SAFECDX-6577 | 108360 | QA: [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:47 | 2025-11-14 07:40
Tuskr | SAFECDX-6576 | 108358 | TUSKR: [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:47 | 2025-11-05 09:21
FE Sub-task | SAFECDX-6575 | 108356 | FE: [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:47 | 2025-11-06 13:35
BE Sub-task | SAFECDX-6574 | 108354 | BE: [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:47 | 2025-11-06 06:45
UI Sub-task | SAFECDX-6573 | 108352 | UI: [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Lucy Duarte | 61d34f77a54af9006960531d | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:47 | 2025-11-02 18:51
Story | SAFECDX-6571 | 108348 | [SafeCDx] - Create a Forms Builder Intro Page | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-11-02 18:20 | 2025-11-19 11:10
Bug | SAFECDX-6570 | 108317 | [SafeCDX] Production ¦ Remove all Internal Admins and Internal Client App Users in Production | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-31 09:44 | 2025-11-06 09:08
AQA | SAFECDX-6569 | 108316 | AQA: [SafeCDx] - Localization - Add Lock Toggle | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:12 | 2025-11-10 08:20
QA | SAFECDX-6568 | 108314 | QA: [SafeCDx] - Localization - Add Lock Toggle | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:12 | 2025-11-13 10:39
Tuskr | SAFECDX-6567 | 108312 | TUSKR: [SafeCDx] - Localization - Add Lock Toggle | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:12 | 2025-11-04 02:17
FE Sub-task | SAFECDX-6566 | 108310 | FE: [SafeCDx] - Localization - Add Lock Toggle | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:12 | 2025-11-07 09:24
BE Sub-task | SAFECDX-6565 | 108308 | BE: [SafeCDx] - Localization - Add Lock Toggle | Jeff Miller | 61f19934aeaacb007209706b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:12 | 2025-11-03 16:43
UI Sub-task | SAFECDX-6564 | 108306 | UI: [SafeCDx] - Localization - Add Lock Toggle | Lucy Duarte | 61d34f77a54af9006960531d | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:11 | 2025-10-31 09:17
Task | SAFECDX-6563 | 108304 | [SafeCDx] - Remove ZIPKIN form SafeCDX | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:04 | 2025-11-03 14:43
Story | SAFECDX-6562 | 108303 | [SafeCDx] - Localization - ORGADMIN - Add custom fields for support and no-reply emails | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 09:03 | 2025-11-19 11:10
AQA | SAFECDX-6561 | 108302 | AQA: [SafeCDx] - Update Localization Terminology on Hamburger Menu | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 08:33 | 2025-11-10 07:55
QA | SAFECDX-6560 | 108300 | QA: [SafeCDx] - Update Localization Terminology on Hamburger Menu | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 08:32 | 2025-11-06 08:21
Tuskr | SAFECDX-6559 | 108298 | TUSKR: [SafeCDx] - Update Localization Terminology on Hamburger Menu | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 08:32 | 2025-11-04 02:09
FE Sub-task | SAFECDX-6558 | 108296 | FE: [SafeCDx] - Update Localization Terminology on Hamburger Menu | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 08:29 | 2025-11-06 06:45
BE Sub-task | SAFECDX-6557 | 108294 | BE: [SafeCDx] - Update Localization Terminology on Hamburger Menu | Veer.Singh | 624744c3247a4b00691e47d0 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 08:20 | 2025-11-06 06:45
UI Sub-task | SAFECDX-6556 | 108292 | UI: [SafeCDx] - Update Localization Terminology on Hamburger Menu | Lucy Duarte | 61d34f77a54af9006960531d | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 08:19 | 2025-10-31 08:41
Epic | SAFECDX-6553 | 108287 | [SafeCDx] - Integrated Testing by Sprint Release 5.1 | Ranjith Gunasekaran | 712020:43427ac6-5629-4a58-80bb-1794d92364ab | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done | Done | 2025-10-31 06:23 | 2025-11-18 14:05
Task | SAFECDX-6552 | 108286 | Change address in Privacy Policy and Terms of Service (English Only) | Jeff Miller | 61f19934aeaacb007209706b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 06:17 | 2025-11-03 16:46
Story | SAFECDX-6551 | 108284 | [SafeCDx] - Localization - Categorization of the Substitutions Menu | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 06:12 | 2025-11-19 11:10
Story | SAFECDX-6550 | 108282 | [SafeCDx] - Localization - SYSADMIN - Add custom fields for support and no-reply emails | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 06:12 | 2025-11-19 11:10
Story | SAFECDX-6549 | 108279 | [SafeCDx] - Localization - Add Lock Toggle | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 05:32 | 2025-11-19 11:10
Task | SAFECDX-6548 | 108278 | [SafeCDx] - Convert OpenCDXIdentifier to ObjectID for MongoDB | Jeff Miller | 61f19934aeaacb007209706b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 04:56 | 2025-11-19 11:09
Story | SAFECDX-6547 | 108277 | [SafeCDx] - Update Localization Terminology on Hamburger Menu | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-31 04:09 | 2025-11-12 06:32
QA | SAFECDX-6546 | 108268 | Test History | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:17 | 2025-11-18 15:47
QA | SAFECDX-6545 | 108267 | Content Studio | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:17 | 2025-11-18 21:35
QA | SAFECDX-6544 | 108266 | Localization - Confirmation of Translated File | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:17 | 2025-11-20 13:38
QA | SAFECDX-6543 | 108265 | Localization - Upload of CSV File | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 15:35
QA | SAFECDX-6542 | 108264 | Localization - Translation of CSV File | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-20 08:23
QA | SAFECDX-6541 | 108263 | Localization - Download of CSV File | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 15:12
QA | SAFECDX-6540 | 108262 | Validate Forms Builder Templates | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 21:35
QA | SAFECDX-6539 | 108261 | Validate Form Builder Questionnaire | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 21:50
QA | SAFECDX-6538 | 108260 | Validate Configuration Library: Sign Up Fields | Loga P | 5dd23b0fb3a9c80fc0a2efb7 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 21:36
QA | SAFECDX-6537 | 108259 | Validate Configuration Library: Language | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 14:11
QA | SAFECDX-6536 | 108258 | Validate Configuration Library: CVML Status | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 14:10
QA | SAFECDX-6535 | 108257 | Validate Configuration Library: Analysis Engine | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-18 14:08
Task | SAFECDX-6534 | 108256 | Staging Configuration After BE Deployment | Samantha Toolsie | 61a802e3c15977006ae1f840 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-30 08:16 | 2025-11-20 13:39
Bug | SAFECDX-6488 | 108181 | [Safecdx] Admin Console - Localization ¦ The application should display an Error Message when uploading a file with Duplicate Keys | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-29 08:11 | 2025-11-19 13:38
Task | SAFECDX-6487 | 108176 | BE Unit Tests | Jeff Miller | 61f19934aeaacb007209706b | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-10-28 13:16 | 2025-11-03 11:04
Task | SAFECDX-6482 | 108153 | [SafeCDX] FE Tech Debt - Unique ID creation for all components | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Ranjith Gunasekaran | 712020:43427ac6-5629-4a58-80bb-1794d92364ab | Low | Done |  | 2025-10-27 08:16 | 2025-11-04 06:32
Bug | SAFECDX-6444 | 108078 | [SafeCDX] Admin Console - Localization ¦ The application should not display 'Dirty Fields' After uploading a completed File | Jeff Miller | 61f19934aeaacb007209706b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-24 13:18 | 2025-11-13 07:17
Bug | SAFECDX-6441 | 108071 | [SafeCDX] Admin Console - Localization ¦ The application is Adding all the Screens from Content Studio in the Dirty Fields if the Admin make Edit to only 1 Screen | Jeff Miller | 61f19934aeaacb007209706b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-24 13:01 | 2025-11-13 07:17
Bug | SAFECDX-6440 | 108069 | [SafeCDX] Questionnaire Null pointer in user map | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Patrick Chou | 61e3a23bb134e80070eec4d3 | Low | Done |  | 2025-10-24 12:50 | 2025-11-19 12:17
Bug | SAFECDX-6435 | 108051 | [SafeCDX] Admin Console - Localization ¦ The application should not display 'English' on the Language Menu Option in the Translation screen | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Samantha Toolsie | 61a802e3c15977006ae1f840 | Medium | Done |  | 2025-10-23 15:32 | 2025-11-05 19:07
Bug | SAFECDX-6433 | 108047 | [SafeCDX] Admin Console - Sys Admin Admin - Localization ¦ The application should not display the Language Field when the 'Row Reference Details' is expand on the 'Expanded View' Pop up | Karthick Rajamurugan | 624eeafaa629c30068a9828a | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-23 14:52 | 2025-11-06 09:11
Bug | SAFECDX-6412 | 107968 | [SafeCDX] Client App - Mobile Web - Take a Test - Localization ¦ The application should display the Drug Names in Spanish language on the Test Result Screen and Test Record | Aditya Patel | 712020:329d9a26-0a33-4bdc-84bb-845a10d572db | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-22 08:31 | 2025-11-06 15:12
Bug | SAFECDX-6392 | 107913 | [SafeCDX] Client App - Mobile Web - Take a Test - Localization ¦ The application should display any Error Message in Spanish language if user selected Spanish as their Language | Yevhenii Pidopryhora | 712020:a303c81a-944f-4f36-8595-f8a3227e459b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-21 13:04 | 2025-11-12 14:20
Bug | SAFECDX-6390 | 107907 | [SafeCDX] Client App - Mobile Web - Take a Test - Localization ¦ The application should display the 'Accessing Camera' text in Spanish Language when accessing the Camera for QR Scan | Patrick Chou | 61e3a23bb134e80070eec4d3 | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-21 12:27 | 2025-11-13 10:21
Bug | SAFECDX-6334 | 107763 | [SafeCDX] Admin Console - Localization ¦ The application should reflect any new entries(screens) made in Content Studio or Forms Builder on the 'Review All Empty Fields' screen. | Jeff Miller | 61f19934aeaacb007209706b | Samantha Toolsie | 61a802e3c15977006ae1f840 | High | Done |  | 2025-10-17 13:25 | 2025-11-12 12:58
Epic | SAFECDX-6320 | 107596 | Localization Enhancements | Leslie Swain | 63f4d9734c355259db9cb748 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done | Done | 2025-10-13 09:13 | 2025-11-19 11:11
AQA | SAFECDX-5833 | 105481 | AQA: [SafeCDx] - Clean up Admin Console MFA Components | Surendra Kumar | 61a9bc999615eb006f551eb4 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Done |  | 2025-07-16 16:31 | 2025-11-19 05:56
Task | SAFECDX-6651 | 108716 | [SafeCDx] - Staging Security Scan | Luis Simonet | 606f2db620947c0069697ed2 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | To Do |  | 2025-11-14 11:25 | 2025-11-14 11:39
Epic | SAFECDX-6495 | 108211 | [SafeCDx] Release 5.1.0 Readiness | Luis Simonet | 606f2db620947c0069697ed2 | Leslie Swain | 63f4d9734c355259db9cb748 | Low | To Do |  | 2025-10-30 07:21 | 2025-11-17 03:35
Task | SAFECDX-6616 | 108547 | Add Environment Variables to the deployment for workspace selection | Jeff Miller | 61f19934aeaacb007209706b | Ranjith Gunasekaran | 712020:43427ac6-5629-4a58-80bb-1794d92364ab | Low | Will Not Implement |  | 2025-11-07 07:36 | 2025-11-19 11:03
DEVOPS Sub-task | SAFECDX-6502 | 108216 | Adding custom attribute language to signup | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Will Not Implement |  | 2025-10-30 07:24 | 2025-11-21 08:42
DEVOPS Sub-task | SAFECDX-6501 | 108215 | New Lambda for sending Emails | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Will Not Implement |  | 2025-10-30 07:24 | 2025-11-21 08:42
DEVOPS Sub-task | SAFECDX-6500 | 108214 | New Email Template - S3 Bucket | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Will Not Implement |  | 2025-10-30 07:24 | 2025-11-21 08:42
DEVOPS Sub-task | SAFECDX-6499 | 108213 | Ensure new Kafka Topic for MFA has been added | Ranga Lakshminarayanan | 617ae659892c4200728ff50f | Leslie Swain | 63f4d9734c355259db9cb748 | Low | Will Not Implement |  | 2025-10-30 07:23 | 2025-11-21 08:42
MBI | SAFECDX-6162 | 106806 | [SafeCDx] - Localization |  |  | Leslie Swain | 63f4d9734c355259db9cb748 | Low | In Development |  | 2025-09-09 10:12 | 2025-11-17 03:35